## Phase_Task_Breakdown
Phase | Task Description | Subtasks | Total Hours
A. Project Kickoff & Setup | A.1 Data Ingestion – Load “Hospital_General_Information.csv” into Power BI Desktop, inspect all 38 columns. | Verify encoding, delimiters, and column types Rename columns to remove spaces/slashes Set data source privacy levels Verify “Refresh Preview”. This is to be done in Power Bi Services | 10
B. Data Transformation & Cleaning | B.1 Power Query: Basic Cleaning – Clean rating and categorical fields, validate ZIP/State. | Replace non-numeric ratings with blank and convert to integer Standardize EmergencyServices to Yes/No Null-encode Birthing Friendly Validate ZIP and State codes. | 10
B. Data Transformation & Cleaning | B.2 Power Query: Nested/Derived Fields – Create lookup tables for State, County, Type, Ownership. | Create lookup tables for State, County/Parish, HospitalType, HospitalOwnership Unpivot performance domain counts into a separate table Trim whitespace from text fields. | 10
C. Data Modeling & Relationships | C.1 Build Star Schema – Hospital fact table + lookup tables (State, County, Type, Ownership, PerformanceDomain). | Identify primary key FacilityID Create Hospital table with cleaned columns Create and link lookup tables Build bridge/unpivot for domain-level measures if needed. | 15
D. DAX Calculations & Measures | D.1 Basic KPIs – Number of Hospitals, Average Overall Rating, % with Emergency, % Birthing-Friendly, counts by HospitalType. | Create TotalHospitals, AvgOverallRating, PctEmergency, PctBirthingFriendly, HospitalsByType measures using DAX. | 8
D. DAX Calculations & Measures | D.2 Domain-Specific Measures – For each domain (MORT, Safety, READM, Pt Exp, TE), compute %Better, %NoDifferent, %Worse. | Define DAX measures PctDBetter, PctDNoDifferent, PctDWorse for each domain using SUM and DIVIDE functions. | 7
E. “What-If” Scenario Modeling | E.1 Rating & Performance Thresholds – Create “What-If” parameters: RatingThreshold, SafetyImprovementPct, ReadmitImprovementPct. | Define parameters using GENERATESERIES Create HospitalsAboveThreshold DAX Create ProjectedSafetyBetter and ProjectedReadmitBetter measures. | 20
F. Visualization & UX Design | F.1 Build Report Pages – Four pages: Overview, Geographic Analysis, Performance Measure Details, Scenario Insights. | Design each page with appropriate visuals: KPI cards, map, bar charts, clustered bars, matrix, line and bar charts Add slicers and filters. | 25
F. Visualization & UX Design | F.2 Interactivity & Tooltips – Drill-through, custom tooltips, bookmarks. | Implement drill-through actions Create custom tooltips for map bubbles Configure bookmarks for default and optimistic scenarios. | 10
G. Testing, QA & Optimization | G.1 Data Validation & DAX Testing – Compare DAX vs. Power Query aggregations, verify “What-If” outputs. | Cross-verify sample hospitals Confirm scenario outputs match manual calculations Test parameters Validate data refresh. | 10
G. Testing, QA & Optimization | G.2 Performance Tuning – Optimize data model, remove unused columns, tune visuals. | Hide unused columns Group rare categories Refactor complex DAX Pre-filter visuals to reduce row scans. | 5
H. Documentation & Deployment | H.1 User Guide & Technical Documentation – Create PDF and Word docs describing data model, DAX formulas, “What-If” steps, and report usage. | User Guide: data refresh, page navigation, slicers Technical Doc: ERD, DAX code, Power Query steps, extension instructions. | 10
H. Documentation & Deployment | H.2 Publish to Power BI Service – Upload .pbix, set permissions, schedule refresh. | Upload file Assign Editor/Viewer roles Configure scheduled refresh Share link with stakeholders.
I. Team Coordination & Meetings | I.1 Sprint Planning & Stand-ups – Kickoff, weekly stand-ups, mid-sprint review, final demo, retrospective. | Kickoff (2h) Weekly stand-ups (1.5h) Mid-sprint review (2h) Final demo (2h) Retrospective (2.5h). | 10

## Effort_Allocation
Learner | Assignments | Total Hours
L1 | A.1 Data Ingestion (10 h) B.1 Basic Cleaning (4 h) C.1 Star Schema Setup (5 h) D.1 Basic KPIs (5 h) H.1 User Guide (4 h) I.1 Coordination (2 h) | 30
L2 | B.2 Lookup Tables (10 h) C.1 Schema Setup (5 h) D.2 Domain Measures (7 h) F.1 Overview & Geo Analysis visuals (8 h) I.1 Coordination (2 h) | 30
L3 | C.1 Schema Setup (5 h) D.2 Domain Measures (3 h) E.1 What-If Modeling (10 h) F.1 Performance Details (5 h) G.1 Data Validation (3 h) I.1 Coordination (2 h) | 30
L4 | E.1 What-If Scenarios (10 h) F.1 Scenario Insights (10 h) F.2 Interactivity & Tooltips (5 h) G.2 Tuning (3 h) I.1 Coordination (2 h) | 30
L5 | B.1 Basic Cleaning support (6 h) F.1 Overview & Geo enhancements (7 h) G.1 QA (4 h) H.1 Technical Documentation (2 h) I.1 Coordination (1 h) F.1 Performance Details support (10 h) | 30

## Timeline
Week | Milestone/Deliverables
Week 1 | Kickoff: L1 imports CSV, verifies column Data Cleaning: L1, L2, L5 finish cleaning and lookup tables Initial Schema: L1, L2, L3 set up star schema
Week 2 | DAX Measures: L1, L2, L3 create KPIs & domain metrics What-If Setup: L3, L4 build parameters & scenario measures UI Skeleton: L2, L3, L5 draft Overview & Geo Analysis pages
Week 3 | Visualization Refinement: L2, L3, L4, L5 finalize pages & interactivity Testing & QA: L2, L3, L4, L5 validate DAX & tune performance Documentation & Publish: L1, L2, L5 finalize guides, publish to Power BI Service, final demo & retrospective

## Key_Deliverables
Deliverable | Details
Cleaned & Transformed Tables | Hospital fact table and lookup tables for State, County, HospitalType, HospitalOwnership, PerformanceDomain, with all cleaning steps applied.
Star Schema Data Model | Relationships linking Hospital to State, County, HospitalType, HospitalOwnership, and optionally PerformanceDomain if using a bridge table.
DAX Measures | Basic KPIs: TotalHospitals, AvgOverallRating, PctEmergency, PctBirthingFriendly, HospitalsByType; Domain metrics for each performance domain.
“What-If” Scenario Measures | RatingThreshold, ProjectedSafetyBetter, ProjectedReadmitBetter measures based on user-selected parameter sliders.
Power BI .pbix Report | Four report pages: Overview, Geographic Analysis, Performance Measure Details, Scenario Insights; plus a drill-through page for hospital details.
Documentation | User Guide PDF for report navigation and refresh; Technical Doc with ERD, DAX code, Power Query steps, and extension instructions.
Published Workspace | .pbix uploaded to Power BI Service, permissions set, scheduled refresh configured, link shared with stakeholders.

## How_to_Use_Plan
Step | Details
Sprint Kickoff (Day 1) | L1 imports CSV, verifies columns. Review roles and responsibilities. Create shared folder with data and project materials.
Daily Stand-ups | Each learner shares progress, plans, and blockers. Update Scrum-board or Teams channel.
Mid-Sprint Review (End of Week 2) | Demo cleaned tables, star schema, KPIs, and initial What-If scenarios; collect feedback.
Final Demo & Handover (End of Week 3) | Present full dashboard, walk through documentation, publish to Power BI Service, confirm scheduled refresh.
Retrospective | Identify successes and areas for improvement; document lessons learned in technical doc.